## UI changes
Section | Hour | Page desc | Page screenshot | What should be done |  |  |  | html | implement in angular in hr | Counter
Sign up | 2hr | Sign up section | https://prnt.sc/zdKanzWE9_Ez | https://www.loom.com/share/0a6c399cb3364d66ae17e7d53b7694e6 |  |  |  | 6 | 3
| 4hr |  | https://prnt.sc/CehETHJLOYHW
[7 empty] | 2 | 1
Infl side | 4hr | Inf signup flow | https://prnt.sc/mdIwKzImrXcu | https://www.loom.com/share/8aa271748d664bb5bfac70ea564a1659 |  |  |  | 2 | 1
| 3hr |  | https://prnt.sc/cMjxKLxFMStA |  |  |  |  | 2 | 1
| 1hr |  | https://prnt.sc/U65hQQ_CbDEx |  |  |  |  | 2 | 1
| 1hr | verify channel | https://prnt.sc/rDYYEy89lHn7 | https://www.loom.com/share/a78f674964de4481bd91ca2d69cd18e2 |  |  |  | 2 | 1
| 13hr | Dashboard | https://prnt.sc/lTW7i0kucmR0 | https://www.loom.com/share/add3a5a9a82b4369b0840f9e68affb90 |  |  |  | 2 | 1
| 3hr | Add channel | https://prnt.sc/EBEIvEIOO0JU | https://www.loom.com/share/c5b8cc16b9664a2caf6c1a1748950f81 |  |  |  | 2 | 1
| 4hr | Public Profile | https://prnt.sc/GPSmMpD1miDN Ref https://www.bookmyinfluencers.com/bmi/influencers/profile.php?channel=UCk0rD4bhbSNnjYx09FPkXig | https://www.loom.com/share/ad1e67c066fc4be5aa6ecdfe09817cc3 |  |  |  | 6 | 2
| 7hr | Campaigns | https://prnt.sc/bj2Ch8u3UCUW | inf side- https://prnt.sc/yZmkTRJYZ4yi | https://www.loom.com/share/6096baf3f5e14d3a9d1a508876d4a42b | https://www.loom.com/share/a20a9b5c25a049e2bfcd9f5d8ee545a9 | https://www.loom.com/share/56b34f05cd2441699d3d812c109ee6ec | https://www.loom.com/share/6c74c8ffe564462195138517fafdf8cc | 2
| 5hr | Proposals | https://prnt.sc/luqidzHAWh9- | https://www.loom.com/share/5956af11d2494d0aa02828bf174ddec9 | https://prnt.sc/7O1b-Wa-1_rB | https://prnt.sc/g6ctVWI37a_- |  | 4 | 1
|  |  | https://prnt.sc/9u7kLiVXmi9U | delete popup can be better |  |  |  | 4 | 2
https://www.loom.com/share/20f3ead4646241128942f1789c866980
| 11hr | Orders | https://prnt.sc/aw7Yg3CNfQyS | inf side https://prnt.sc/HYCNOnebHR1K
|  |  | https://prnt.sc/tCrnFkv5TenS | submit script https://prnt.sc/qvISmJda0H6e
Video preview submit https://prnt.sc/EBVHf0p1FCfB
|  |  |  | Live video https://prnt.sc/vCv5KfCyauFc |  |  |  | 8 | 3
|  | Mgmt Service | https://prnt.sc/fHcv3TGKRRbi |  | Need a Personal Manager at no extra charge for managing your paid collaborations for better values and success rate?
| 4hr |  | https://prnt.sc/mcn6SvXv6jEM | https://www.loom.com/share/dd07f41ab6fe4bb18d490435ed7228c3 | https://prnt.sc/AZL26twDU4vY
|  |  | https://prnt.sc/nyMsppqCsov8 |  | Thanks. We have received your interest for Management service. Our team will be in touch with you shortly.
|  | Settings | https://prnt.sc/mMLY7K1kNXd_ | https://www.loom.com/share/484f62dc4a084ce49ce087ba2546abdb
| 2hr |  | https://prnt.sc/UTU_gHhTRDVy |  |  |  |  | 2 | 1
https://prnt.sc/zHKepYF0QfqW
https://prnt.sc/wBlr4R6518d7
|  | Transaction | https://prnt.sc/g7zriAxZoqTU | https://www.loom.com/share/06d15b0877224a21b274d7782e374fdb |  |  |  | 4 | 2
|  | Chat | https://prnt.sc/0aLwrZjJWbr1
Brand side |  | pricing plan page | https://www.loom.com/share/db45e8f80b514434b4fc082e19515d91 |  |  |  |  | 4 | 1
|  | Dashboard | https://prnt.sc/onFk0TDAmt66 | https://www.loom.com/share/ae40e68fc7194d3088a97b918b49c8ea | channel to reveal https://prnt.sc/IP4xdxa9NmuA Remove show similiar from here | Revealed channel https://prnt.sc/ahKGqASDV0l0 | icons- Crown= Premium Influencer, exclim. mark= one hit wondor, egg= No content, clock= Old content |  |  | not showing names on hover ( pre inf, old videos, one hit wonder)
|  | Show similiar channel |  | Still appearing in old style | [5 empty] | invite cta missing
|  | Post a campaign | https://prnt.sc/Q5u_Y-1_6dZc https://prnt.sc/xiOWJ5OQ16Ms https://prnt.sc/RqmehVZtXvrx https://prnt.sc/bMLM5o3iGVX5 https://prnt.sc/PZZZlSdeJZ5O https://prnt.sc/ebdxl8FSQIfG | https://www.loom.com/share/e7bac70102fb4f9bb1aa64d776b2583e | screen zoom fixes tab issue. | https://prnt.sc/K8ckRio_XJup Website is working fine on 15 inches but creatin issue on 14 in ch screen |  | 10
| 6hr |  |  | https://www.loom.com/share/c8f6b126dfc449dca46f77c88feffc93?focus_title=1&muted=1&from_recorder=1
|  |  |  | https://www.loom.com/share/0718a58295ae45ff9dcdfd132513285f |  | free | starter | 4 | 2
|  |  |  | https://www.loom.com/share/6d3d076f71934ed4b8463721050de8fb?focus_title=1&muted=1&from_recorder=1 | Qualification criteria: Define your target audience | Your listing will be private so your campaign wouldn't be exposed to any influencer by default. Upgrade to expand your default exposure | Your campaign exposure would be limited to Non-premium Influencers only. Upgrade for removing this limitation
|  | Order Section | https://prnt.sc/keU9xARbefZc
|  | raise a dispute pop-up | ?
| 9hr | Campaigns | https://prnt.sc/LWHminWYeXHN | brand- https://prnt.sc/ruZ1dOeHi4Qa pls give a invite list option in this tile which is missing in this design.
|  |  | https://prnt.sc/OFK_UGvytsxc | https://www.loom.com/share/e6acafae2ce541218ce1d4c27f462d6f |  |  |  | 6 | 2
|  | proposals | https://prnt.sc/Soc31DowvXnd | view proposal button popup https://www.loom.com/share/0654cb483a0b407e92308f92faaea16c | https://prnt.sc/ONmo-CONA_un |  |  | 2 | 1
|  |  | https://prnt.sc/ONmo-CONA_un | Unrevealed proposal - new presentation | https://www.loom.com/share/e8b179354fd245fa826bdbab18455190 |  |  | 4 | 1 | not showing dp of influencer who submitted proposal | https://prnt.sc/yM_CpKVAW0cS
|  |  | https://prnt.sc/s2daEPsVR_ku | Revealed proposal - new presentation
|  | Campaign under review' popup | https://www.loom.com/share/46e3d783be2e4806b08f6f7a2bfeb9c3?focus_title=1&muted=1&from_recorder=1 |  |  |  |  | 8 | 3
| 4hr | preview order pop up while hiring an inf | https://prnt.sc/SSCwlvyxu1tT
| 8hr | Invite list
|  | delete | https://prnt.sc/qbBh5sI8wN9J | https://www.loom.com/share/892667f8f5d2468db370c2671dc2a4da |  |  |  | 4 | 1
|  | Revealed Channels | https://prnt.sc/MnQR0SvZRvpZ https://prnt.sc/Qxc-UCdcwxSx
when no channel is revealed yet, just show a simple image with text: "You're yet to reveal any channels yet"
|  | Invite all | https://prnt.sc/sCeREU1FMr4d
|  | Favourite channels | https://prnt.sc/QP-nDHJhMSuM | when no channel is favourited yet, just show a simple image with text: "You're yet to mark any favourites"
|  | Settings | https://prnt.sc/VM-b8icOx74N https://prnt.sc/pic9sC-pSq_- https://prnt.sc/YTIkMdmkWcqn | https://www.loom.com/share/b43815a7f1c94904911714e48cd7dc0b?focus_title=1&muted=1&from_recorder=1 |  |  |  | 10 | 2
| 2hr | My lists | my list ui shoud be made similiar as Reachomation's list section, as described in video | https://www.loom.com/share/071815cbb4b14454864e4fcd488b4d08
|  | Wallet |  | no changes needed
|  | Orders | brand side- https://prnt.sc/Rwj2oeOElTQh
| 9hr |  | review script https://prnt.sc/B5BeyPQ3ODhc
approve video preview https://prnt.sc/pW0gQ2wQeTxz
Live video approval- https://prnt.sc/xwcJdmpCBupO
|  | low on balance while hiring an inf | https://prnt.sc/4UIiPkK_6017
| 5hr | Deal terms | https://prnt.sc/R5adjY6THA8T
| 3hr | "Reveal All" popup | https://prnt.sc/J-5g03wyPE26
| 4hr | Approve order stage changes- View options for Campaign resource, Script, Preview(Link only), Live (Link only)
| 3hr | cta in left menu Contact Relationship Manager- which will open a pop up (brand side)
| 4hr | messaging alignment
| 1hr | crispchat alignment
| 3hr | Original deadline with i button
| 2hr | remove dotted borders,remove work,Show similar #D4DBE1 Reveal #41F4D8 Invite/Hire [Orange] history,invite, hire, reveal,show similar aren't appearing as CTA
Instagram account display (hidden and revealed)
New Pages
| 4hr | Campaign resource page after order payment | https://prnt.sc/XZnJzhE4jBYE
|  | landing page after Campaign creation | Free- https://prnt.sc/eEDj7xM88Hx9
Starter- https://prnt.sc/z-t2W73ddRJu
| 2hr |  | Business- https://prnt.sc/zlgMDNjwL_pO
| 2hr | preview order pop up while hiring an inf | https://prnt.sc/SSCwlvyxu1tT
minor changes
|  | 7:23 to 7:25 showing blank channel suggetions | https://www.loom.com/share/0b457ad2416b4c2184e36d3c6b34d387
Note on A1: Abhishek kumar Singh:

## Abhishek Design
https://prnt.sc/zdKanzWE9_Ez
https://prnt.sc/CehETHJLOYHW
https://prnt.sc/mdIwKzImrXcu
https://prnt.sc/cMjxKLxFMStA
https://prnt.sc/U65hQQ_CbDEx
https://prnt.sc/rDYYEy89lHn7
https://prnt.sc/lTW7i0kucmR0
https://prnt.sc/EBEIvEIOO0JU
https://prnt.sc/bj2Ch8u3UCUW
https://prnt.sc/luqidzHAWh9-
https://prnt.sc/aw7Yg3CNfQyS
https://prnt.sc/tCrnFkv5TenS
https://prnt.sc/fHcv3TGKRRbi
https://prnt.sc/mcn6SvXv6jEM
https://prnt.sc/nyMsppqCsov8
https://prnt.sc/mMLY7K1kNXd_
https://prnt.sc/UTU_gHhTRDVy
https://prnt.sc/zHKepYF0QfqW
https://prnt.sc/wBlr4R6518d7
https://prnt.sc/g7zriAxZoqTU
https://prnt.sc/0aLwrZjJWbr1
https://prnt.sc/onFk0TDAmt66
https://prnt.sc/Q5u_Y-1_6dZc
https://prnt.sc/xiOWJ5OQ16Ms
https://prnt.sc/RqmehVZtXvrx
https://prnt.sc/bMLM5o3iGVX5
https://prnt.sc/PZZZlSdeJZ5O
https://prnt.sc/ebdxl8FSQIfG"
https://prnt.sc/keU9xARbefZc?
https://prnt.sc/LWHminWYeXHN
https://prnt.sc/OFK_UGvytsxc
https://prnt.sc/Soc31DowvXnd
https://prnt.sc/ONmo-CONA_un
https://prnt.sc/s2daEPsVR_ku
https://prnt.sc/SSCwlvyxu1tT
https://prnt.sc/qbBh5sI8wN9J
https://prnt.sc/MnQR0SvZRvpZ
https://prnt.sc/Qxc-UCdcwxSx"
https://prnt.sc/sCeREU1FMr4d
https://prnt.sc/QP-nDHJhMSuM
https://prnt.sc/VM-b8icOx74N
https://prnt.sc/pic9sC-pSq_-
https://prnt.sc/YTIkMdmkWcqn"
brand side- https://prnt.sc/Rwj2oeOElTQh
review script https://prnt.sc/B5BeyPQ3ODhc
approve video preview https://prnt.sc/pW0gQ2wQeTxz
Live video approval- https://prnt.sc/xwcJdmpCBupO
https://prnt.sc/4UIiPkK_6017
https://prnt.sc/R5adjY6THA8T
https://prnt.sc/J-5g03wyPE26
https://prnt.sc/XZnJzhE4jBYE
Free- https://prnt.sc/eEDj7xM88Hx9
Starter- https://prnt.sc/z-t2W73ddRJu
Business- https://prnt.sc/zlgMDNjwL_pO
forget password
reset password
cta in left menu Contact Relationship Manager- which will open a pop up (brand side)
messaging alignment
crispchat alignment
https://prnt.sc/qvISmJda0H6e
camp graph
camp edit

## Workfile name
src/app/modules/admin/apps/list/details/details.component.html
src/app/modules/admin/apps/list/list.component.html
src/app/modules/admin/pages/settings/personal-information/personal-information.component.html
src/app/modules/admin/pages/settings/billing/billing.component.html
src/app/modules/admin/pages/settings/account/account.component.html
src/app/modules/admin/pages/settings/payment/payment.component.html
src/app/layout/ommon/invite-influencer-popup/invite-influencer-popup.component.html
src/app/modules/admin/pages/profile/profile.component.html
src/app/modules/auth/ign-up-step-two/sign-up-step-two.component.html
src/app/modules/admin/apps/saved-channels/saved-channels.component.html
src/app/modules/admin/apps/management-services/management-services.component.html
src/app/layout/common/influencer-channel/influencer-channel.component.html
src/app/layout/common/order-list/order-list.component.html
src/app/layout/common/order-progress-bar/order-progress-bar.component.html
src/app/layout/common/order-progress-bar/order-progress-bar.component.scss
src/app/layout/common/single-campaign/single-campaign.component.html
src/app/modules/admin/apps/orders/campaign-resource-preview/campaign-resource-preview.component.html
src/app/modules/admin/apps/orders/details/details.component.html
src/app/modules/admin/apps/orders/review-video/review-video.component.html
src/app/modules/admin/apps/orders/upload-video/upload-video.component.html
suggested-invite-list.component.html
post.component.html
hire-confirmation-popup.component.html
reset-password.component.html
forgot-password.component.html
src/app/layout/common/verify-channel-popup/verify-channel-popup.component.html
src/app/modules/admin/apps/add-channel/add-channel.component.html
src/app/modules/auth/sign-in/sign-in.component.html
src/app/modules/auth/sign-up/sign-up.component.html
src/app/layout/common/influencer-welcome-popup/influencer-welcome-popup.component.html
src/app/layout/common/information-review-popup/information-review-popup.component.html
src/app/layout/common/payment-guidelines-popup/payment-guidelines-popup.component.html
src/app/modules/admin/apps/campaigns/responses/responses.component.html
src/app/modules/admin/apps/management-services/features/features.component.html
src/app/modules/admin/apps/revealed-channels/revealed-channels.component.html
src/app/layout/common/relation-manager/
src/app/layout/common/quick-chat/quick-chat.component.html
src/app/layout/common/quick-chat/quick-chat.component.scss
src/app/mock-api/common/navigation/api.ts
src/app/mock-api/common/navigation/data.ts
src/app/modules/admin/apps/chat/chats/chats.component.html

## Text changes (hidden)
| from | To
Brand - settings | Update your billing information. Make sure to set your billing details correctly as it could affect your payment. | Update your billing information. Make sure to set your billing details correctly as it could affect your invoices and GST credits
| Communication details in case we want to connect with you. These will be kept private. | Your account manager will use this info to connect and assist you in any possible manner.
| Profile Following information is publicly displayed, be careful! | delete

## New pagespopupselements (hidden)
desc | Youtube |  | Instagram
Campaign resource page after order payment | https://prnt.sc/XZnJzhE4jBYE
landing page after Campaign creation | Free/Starter/Business | Free- https://prnt.sc/eEDj7xM88Hx9 , starter- https://prnt.sc/z-t2W73ddRJu , Business- https://prnt.sc/zlgMDNjwL_pO
Unrevealed Influencer | https://prnt.sc/IP4xdxa9NmuA
Revealed influencer | https://prnt.sc/ahKGqASDV0l0
Campaigns | brand- https://prnt.sc/ruZ1dOeHi4Qa | inf side- https://prnt.sc/yZmkTRJYZ4yi
Proposals | https://prnt.sc/ONmo-CONA_un , after reveal https://prnt.sc/s2daEPsVR_ku | next page where we hire or shortlist
Orders | brand side- https://prnt.sc/Rwj2oeOElTQh | inf side https://prnt.sc/HYCNOnebHR1K
| review script https://prnt.sc/B5BeyPQ3ODhc | submit script https://prnt.sc/qvISmJda0H6e
| approve video preview https://prnt.sc/pW0gQ2wQeTxz | Video preview submit https://prnt.sc/EBVHf0p1FCfB
| Live video approval- https://prnt.sc/xwcJdmpCBupO | Live video https://prnt.sc/vCv5KfCyauFc
preview order pop up while hiring an inf | https://prnt.sc/SSCwlvyxu1tT
low on balance while hiring an inf | https://prnt.sc/4UIiPkK_6017
Deal terms | https://prnt.sc/R5adjY6THA8T
"Reveal All" popup | https://prnt.sc/J-5g03wyPE26
minor changes
7:23 to 7:25 showing blank channel suggetions | https://www.loom.com/share/0b457ad2416b4c2184e36d3c6b34d387

## addl details (hidden)
theme used | https://preview.themeforest.net/item/fuse-angularjs-material-design-admin-template/full_screen_preview/12931855?_ga=2.87112605.447399179.1666793487-1200034068.1625567167
Influencer account
Brand account

## errors after changes (hidden)
Shortlist button is clickable even after shortlisting the influencer in "All" tab. | https://prnt.sc/HxmtItmcbGsn | Done
Invite button is missing in invite list section | https://prnt.sc/0hT_fUGGlq28 | Done
order pages are not as per provided design/texts (https://prnt.sc/HYCNOnebHR1K , https://prnt.sc/Rwj2oeOElTQh) | https://prnt.sc/d9dYBIvlZoe9, https://prnt.sc/vqJEslcDo3jc | Done
Script submit text box not as per design (https://prnt.sc/qvISmJda0H6e) | https://prnt.sc/b8WkWGV3VkHe | Done
Review script is not as per provided design https://prnt.sc/B5BeyPQ3ODhc | https://prnt.sc/LDevY6lmkXSr | Done
brand isn't able to scroll the page while reviewing the script, button are also not visible without decreasing screen size | https://prnt.sc/kGONU1FE4QlH | Done
script download button isn't clickable. |  | Done
Alignment issues both sides | https://prnt.sc/7lNgO8KM8kPu | Done
hyperlink click to view with the link influencer uploaded in both stages ( review video, live video) | https://prnt.sc/eLOVNmVV5fs7 | Done
Escrow balamce is higher than deal value | https://prnt.sc/zzb4g0QZyuMP | Done
not showing the script | https://prnt.sc/0mUiC3E-Iz0A | Done
not showing the comments written by brand for changes | https://prnt.sc/V7ihA_b1QBh9 | Done
not showing promotext amd link given by brand | https://prnt.sc/Rob3XAwVCG1h | Done
not looking good | https://prnt.sc/ZhXuMqzVjUDA , https://prnt.sc/0_s2QNoPtTOC | Done
invite, hire, reveal,show similar aren't appearing as CTA
Show similar #D4DBE1 Reveal #41F4D8 Invite/Hire [Orange] |  | Done
remove work history |  | Done
remove dotted borders |  | Done
Original deadline with i button |  | Done
Approve order stage changes- View options for Campaign resource, Script, Preview(Link only), Live (Link only) |  | Done
cta in left menu Contact Relationship Manager- which will open a pop up (brand side) | https://prnt.sc/nhvnqI_sRJKE | Done
messaging alignment | https://prnt.sc/N7EAk71z68_p | Done
crispchat alignment |  | Done
Data related issue | https://www.loom.com/share/4ff2fd6b2365481d867ec3f53affe17a | Done
Data showing related issue | https://www.loom.com/share/c81291f732464991aad9fe1f8192b4fb | Done
download button isnt working, and not showing the written script | https://prnt.sc/j0Q-y2-rHwdq
payment button isn't working | https://prnt.sc/qZ7Pw6Rem7uQ | api validation issue
broken design | https://prnt.sc/20-DV-EWb407 | Done
showing wrong influencer name | https://www.loom.com/share/fb48228fd9b64eab8e9cbaa24fe1d269 | Api issue

## influencer side review (hidden)
Provided design | Design by Abhishek | Comment
https://prnt.sc/HYCNOnebHR1K | https://prnt.sc/rNin-mz28ROd | Msg button to be change, | Done
https://prnt.sc/R5adjY6THA8T | https://prnt.sc/ALcRNTNrb--q | showing integration time multiple times, that too in complete seconds not s | Done
| https://prnt.sc/eP9UZRxQROjT | while influencer it waiting for script approval, text is wrong (remove your) | Done
| https://prnt.sc/3f14heK0VZ29 | not showing completion dates, msg button to be change | Done
| https://prnt.sc/G-KxKyVYZn7e | not showing complete data without clicking any link/section on the dashboard | Done
| https://prnt.sc/3LERHKgSSbuR |  | Done

## Brand side review (hidden)
Provided design | Design by Abhishek | Comment
https://prnt.sc/ruZ1dOeHi4Qa | https://prnt.sc/ruZ1dOeHi4Qa | Private spelling wrong | Done